## Sheet1
Circle | Site Id | Technology | Status Date | Site Status | Fail KPI | Test Case | Remarks
UW | RKE160_ROR_P45 | L1800 | Nov 8 2025 5:23PM | FAIL | All Sectors-TCP DL (Mbps) All Sectors-Round trip time or Latency(ms) 1st and 2nd Sector-VOLTE setup SR All Sector-Check functioning of ViLTE |  | Static DL All Sectors:The acceptance criteria for L1800 15 MHz sites is 70 Mbps. Please exclude the existing logfile, create a fresh one, and verify that the throughput is above 70 Mbps. Ping All Sectors:Ping was not captured in your logfile. Kindly redo the test and ensure ping results are recorded. 1st and 2nd Sector:Add a VoLTE short-call drive in both Sector 1 and Sector 2. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors VoLTE Video Call (MO):Please do not use WhatsApp for this test case. You must perform a manual VoLTE video call after running the script.
KK | BL0199_BEN_P47 | L2100 | Nov 9 2025 5:20PM | FAIL | 3rd Sector-PCI All Sector-TCP DL (Mbps) All Sector-TCP UL (Mbps) 3rd Sector-Network Detach Success rate All Sectors-Round trip time or Latency(ms) 3rd Sector-CSFB success rate 1st and 2nd Sector-Fast Return Time All Sectors-VOLTE setup SR All Sectors-Check functioning of ViLTE |  | Static All 3rd Sector:Since the serving cell of Sector 2 is stronger than Sector 3, the report is showing Sector 2 PCI. Please exclude the current logfile and redo the test with correct Sector 3 serving PCI. All Sectors – DL and UL Static:For L2100 20 MHz sites, the DL and UL acceptance criteria are 80 Mbps and 20 Mbps respectively. Kindly redo the DL/UL static tests and verify that throughput meets or exceeds the acceptance criteria. 3rd Sector – CLRS:Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 3rd Sector – CSFB MO:There is a drop in CSFB MO for Sector 3. Please exclude the logfile and redo the test. 1st and 2nd Sector – CSFB MO:Fast Return to LTE after CSFB call is not recorded. Exclude the logfile and create a new one. While testing, keep download test files running in the background to ensure fast return to LTE. All Sectors – VoLTE Short Call:Add a VoLTE short-call drive across all sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | BL0199_BEN_P45 | L1800 | Nov 9 2025 6:51PM | FAIL | All Sector-TCP DL (Mbps) All Sector-TCP UL (Mbps) All Sectors-Round trip time or Latency(ms) All Sectors-VOLTE setup SR All Sectors-Check functioning of ViLTE |  | All Sectors – DL and UL Static:For L1800 10 MHz sites, the DL and UL acceptance criteria are 50 Mbps and 16 Mbps respectively. Kindly redo the DL/UL static tests and verify that throughput meets or exceeds the acceptance criteria. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile All Sectors – VoLTE Short Call:Add a VoLTE short-call drive across all sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KL | EKMI75_EKM_P49 | L2300 | Nov 10 2025 3:24PM | FAIL | Multiple KPI fail due to PCI issue |  | The PCI in the Database is not matching with Actual servings of the Site.Kinldy check the database and update
KK | BL0199_BEN_P53 | L900 | Nov 10 2025 4:55PM | FAIL | 2nd and 3rd Sector-DL and UL Peak 1st Sector-Network Detach time(ms),Network Detach Success rate All sectors-Round trip time or Latency(ms) 2nd Sector-Fast Return Time All Sector-Check functioning of ViLTE |  | Static DL and UL 2nd and 3rd Sector- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 1st Sector-CLRS-Detach is not captured in your logfile. Kindly redo the test and verify it in the Event tab before saving the logfile. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 2nd Sector CSFB MO-Fast Return to LTE after CSFB call is not recorded. Exclude the logfile and create a new one. While testing, keep download test files running in the background to ensure fast return to LTE. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KL | MANI21_KOZ_P45 | L1800 | Nov 10 2025 6:05PM | FAIL | ALL Sector-LAC 1st Sector-Pb values for RS power 1st Sector-TCP DL (Mbps) All Sector-Network Detach Success rate All Sector-Round trip time or Latency(ms) 1st and 3rd Sector-VOLTE setup SR All Sectors-Check functioning of ViLTE |  | Static All,Lac is not captured kinldy do some new logfiles in static and verify the LAC . 1st Sector- Static All, PB value is not captured, kindly create new logfiles and verify PB value. 1st Sector-DL static- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. All Sector- CLRS- The Detach Request count is higher than the Detach Accept count. The acceptance criteria require a 100 percent match. Please exclude this logfile, create a new one, and ensure that the Detach Request equals the Detach Accept in the Event tab. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 1st and 3rd Sector – VoLTE Short Call:Add a VoLTE short-call drive across 1st and 3rd sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | BOMH01_TUM_P47 | L2100 | Nov 10 2025 8:37PM | FAIL | All Sectors-TCP DL (Mbps) All Sectors-Round trip time or Latency(ms) 2nd Sector-VOLTE setup SR All Sector-Check functioning of ViLTE 1st Sector-CSFB: MO call set up time,CSFB success rate,Fast Return Time |  | 1st Sector-DL static- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 2nd Sector – VoLTE Short Call:Add a VoLTE short-call drive across 2nd sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script. 1st Sector- CSFB MO- CSFB call setup is not recorded in the 1st sector. Kindly redo the test and verify both the call setup and the fast return to LTE.
KK | BG0184_BEN_P45 | L1800 | Nov 10 2025 10:14PM | FAIL | All Sectors- DL and UL Peak, 3rd Sector-Network Detach Success rate All Sectors-Round trip time or Latency(ms) All Sectors-Check functioning of ViLTE |  | 1st Sector-DL/UL static- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 3rd Sector- CLRS- The Detach Request count is higher than the Detach Accept count. The acceptance criteria require a 100 percent match. Please exclude this logfile, create a new one, and ensure that the Detach Request equals the Detach Accept in the Event tab. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | AANGI1_BIJ_P47 | L2100 | Nov 11 2025 8:54AM | FAIL | 1st Sector-PCI, All Sectors-Round trip time or Latency(ms) All Sectors-Fast Return Time 1st Sector-VOLTE setup SR All Sectors-Check functioning of ViLTE |  | Static All 1st Sector:Since the serving cell of Sector 2 is stronger than Sector 1, the report is showing Sector 2 PCI. Please exclude the current logfile and redo the test with correct Sector 1 serving PCI. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 1st Sector – VoLTE Short Call:Add a VoLTE short-call drive across 1st sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | BOMH01_TUM_P47 | L2100 | Nov 11 2025 2:00PM | FAIL | 2nd and 3rd sector-Round trip time or Latency(ms) 1st Sector-Fast Return Time 2nd Sector-VOLTE setup SR All Sector-Check functioning of ViLTE |  | 2nd and 3rd Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 1st Sector- CSFB MO- UE not retured from 2G to LTE in idle mode after CSFB call. Kindly redo the test and verify both the call setup and the fast return to LTE. 2nd Sector – VoLTE Short Call:Add a VoLTE short-call drive across 2nd sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KL | MANI21_KOZ_P47 | L2100 | Nov 11 2025 3:03PM | FAIL | ALL Sector-LAC All Sector-TCP DL (Mbps) All Sector-Network Detach Success rate All Sector-Round trip time or Latency(ms) All Sectors-Check functioning of ViLTE |  | Static All,Lac is not captured kinldy do some new logfiles in static and verify the LAC . All Sector-DL static- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. All Sector- CLRS- The Detach Request count is higher than the Detach Accept count. The acceptance criteria require a 100 percent match. Please exclude this logfile, create a new one, and ensure that the Detach Request equals the Detach Accept in the Event tab. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KL | MANI21_KOZ_P45 | L1800 | Nov 12 2025 5:20PM | FAIL | 1st Sector-TCP DL (Mbps) All Sectors-Network Detach Success rate All Sectors-Round trip time or Latency(ms) 1st and 3rd Sector-VOLTE setup SR All Sectors-Check functioning of ViLTE |  | 1st Sector-DL static- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. All Sector- CLRS- The Detach Request count is higher than the Detach Accept count. The acceptance criteria require a 100 percent match. Please exclude this logfile, create a new one, and ensure that the Detach Request equals the Detach Accept in the Event tab. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 1st and 3rd Sector – VoLTE Short Call:Add a VoLTE short-call drive across 1st and 3rd sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. All Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KL | MANI21_KOZ_P47 | L2100 | Nov 12 2025 6:14PM | FAIL | All Sector-TCP DL (Mbps) All Sectors-Network Detach Success rate All Sectors-Round trip time or Latency(ms) Sector 1-Volte abnormal release rate |  | All Sector-DL static- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. All Sector- CLRS- The Detach Request count is higher than the Detach Accept count. The acceptance criteria require a 100 percent match. Please exclude this logfile, create a new one, and ensure that the Detach Request equals the Detach Accept in the Event tab. All Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile Sector 1- Volte Short Call MO Drive: There is one call drop in Sector 1 , kindly exclude the logfile with call drop and create new logfile
KL | CHEG01_ALP_P49 | L2300 | Nov 12 2025 6:32PM | FAIL | 2nd Sector-Pb values for RS power 1st Sector-TCP DL (Mbps) and TCP UL (Mbps) Both Sector-Network Detach time(ms), Network Detach Success rate 1st Sector-Round trip time or Latency(ms) Both Sector-CSFB success rate,Fast Return Time Both Sector-Check functioning of ViLTE |  | 2nd Sector- Static All, PB value is not captured, kindly create new logfiles and verify PB value. Static DL and UL 1st Sector- The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. Both Sector – CLRS:Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 1st Sector Ping- The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile Both Sector- CSFB MO- CSFB call setup is not recorded in the 1st sector. Kindly redo the test and verify both the call setup and the fast return to LTE. Both Sectors – VoLTE Video Call (MO):Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | KJRUS1_BEN_P47 | L2100 | 05-Dec-2025 12:24 PM | FAIL | 1. PCI 2. RSRP (Average Value) 3. SINR (Average Value) 4. Session establishment time(ms) 5. TCP UL (Mbps) 6. Network Detach Success rate 7. Round trip time or Latency(ms) 8. CSFB: MO call set up time 9. CSFB: MT call set up time 10. Fast Return Time | 1. Static All 2. Drive DL Ftp 3. Drive DL Ftp 4. Static ATDT 5. Static UL 6. Static Cell Reselection 7. Static Ping 8. Static CSFB MO 9. Static CSFB MT 10. Static CSFB MO | 1. Since the serving cell of the failed sector is different from the recorded PCI, the report is displaying the recorded PCI as the failed sector. Please exclude the current logfile and redo the test with the correct serving PCI. 2. It appears that the PCI recorded in the site database does not match the actual serving PCI observed on the site, or the failed sector has no corresponding drive data. Request you to please verify the serving cells in the DL drive along with the PCI details in the site database. 3. It appears that the PCI recorded in the site database does not match the actual serving PCI observed on the site, or the failed sector has no corresponding drive data. Request you to please verify the serving cells in the DL drive along with the PCI details in the site database. 4. Session Abnormal Release Rate failed due to RLF, poor RF conditions, S1/backhaul instability, handover failures, or hardware issues. Improve RF coverage, verify S1 link, optimize HO parameters, and fix hardware/transport faults to reduce abnormal releases.Exclude ATDT in failed Sector and Redo again. 5. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 6. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 7. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 8. MO CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 9. MT CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 10. Reselection Time After CSFB Call Idle to LTE (ms)
KK | CHKBD2_BLG_P47 | L2100 | 06-Dec-2025 11:09 AM | FAIL | 1. Pb values for RS power 2. TCP DL (Mbps) 3. TCP UL (Mbps) 4. Network Detach Success rate 5. Round trip time or Latency(ms) 6. CSFB success rate | 1. Static All 2. Static DL 3. Static UL 4. Static Cell Reselection 5. Static Ping 6. Static CSFB MO | 1. PB value is not captured, kindly create new logfiles and verify PB value. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 3. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 4. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 5. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 6. CSFB MO Success Rate failed because the Call Setup Time is above the acceptance criteria, or there are blocked/unsuccessful calls, or fewer than 3 successful calls were completed. Kindly redo the test ensuring CST is within limits and at least 3 MO CSFB calls are successfully established.
KK | BL0199_BEN_P53 | L900 | 06-Dec-2025 1:55 PM | FAIL | 1. TCP DL (Mbps) 2. TCP UL (Mbps) 3. Network Detach time(ms) 4. Network Detach Success rate 5. Round trip time or Latency(ms) 6. Fast Return Time 7. Check functioning of ViLTE | 1. Static DL 2. Static UL 3. Static Cell Reselection 4. Static Cell Reselection 5. Static Ping 6. Static CSFB MO 7. Static Video call MO | 1. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 3. The Detach Request count is higher than the Detach Accept count. The acceptance criteria require a 100 percent match. Please exclude this logfile, create a new one, and ensure that the Detach Request equals the Detach Accept in the Event tab. 4. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 5. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 6. Reselection Time After CSFB Call Idle to LTE (ms) 7. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
UW | RNDT01_BAR_P49 | L2300 | 06-Dec-2025 4:39 PM | FAIL | 1. TCP DL (Mbps) 2. Round trip time or Latency(ms) 3. VOLTE setup SR 4. Check functioning of ViLTE | 1. Static DL 2. Static Ping 3. Drive Volte SCMO 4. Static Video call MO | 1. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 2. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 3. Add a VoLTE short-call drive across all sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. 4. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
GJ | 864941_GJ_P47 | L2100 | 06-Dec-2025 6:34 PM | FAIL | 1. TCP DL (Mbps) 2. TCP UL (Mbps) 3. Round trip time or Latency(ms) 4. VOLTE setup SR | 1. Static DL 2. Static UL 3. Static Ping 4. Drive Volte SCMO | 1. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 3. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 4. Add a VoLTE short-call drive across all sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup.
UW | KMUR01_MIN_P49 | L2300 | 06-Dec-2025 6:50 PM | FAIL | 1. TCP DL (Mbps) 2. TCP UL (Mbps) 3. Network Detach Success rate 4. Round trip time or Latency(ms) 5. VOLTE setup SR 6. Check functioning of ViLTE 7. Volte abnormal release rate , drop rate . Mention the cause code of abnormal release | 1. Static DL 2. Static UL 3. Static Cell Reselection 4. Static Ping 5. Drive Volte SCMO 6. Static Video call MO 7. Drive Volte SCMO | 1. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 3. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 4. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 5. Add a VoLTE short-call drive across all sectors. Do not disconnect the call manually, as it will be counted as a call drop. Each sector must have at least one successful MO session setup. 6. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script. 7. There is a call drop in the failed sector. Kindly exclude the affected logfile, create a new logfile, and redo the test to verify successful call completion with no drops.
UW | SHWL01_MOR_P49 | L2300 | 06-Dec-2025 8:29 PM | FAIL | 1. Session set up success rate 2. TCP DL (Mbps) 3. TCP UL (Mbps) 4. Round trip time or Latency(ms) 5. CSFB: MO call set up time 6. Check functioning of ViLTE 7. Volte abnormal release rate , drop rate . Mention the cause code of abnormal release | 1. Static ATDT 2. Static DL 3. Static UL 4. Static Ping 5. Static CSFB MO 6. Static Video call MO 7. Drive Volte SCMO | 1. Session Setup Success Rate failed due to RRC/S1 signaling issues, poor RF conditions, PRACH failures, TAC mismatch, or MME congestion. Verify RF coverage, PRACH performance, S1 link stability, TAC configuration, and MME capacity to improve success rate. Exclude ATDT in failed Sector and Redo again. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 3. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 4. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 5. MO CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 6. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script. 7. There is a call drop in the failed sector. Kindly exclude the affected logfile, create a new logfile, and redo the test to verify successful call completion with no drops.
KK | KJRUS1_BEN_P47 | L2100 | 08-Dec-2025 10:26 AM | FAIL | 1. Session establishment time(ms) 2. TCP UL (Mbps) 3. Network Detach Success rate 4. Round trip time or Latency(ms) 5. CSFB: MO call set up time 6. CSFB: MT call set up time 7. Fast Return Time 8. Check functioning of ViLTE | 1. Static ATDT 2. Static UL 3. Static Cell Reselection 4. Static Ping 5. Static CSFB MO 6. Static CSFB MT 7. Static CSFB MO 8. Static Video call MO | 1. Session Abnormal Release Rate failed due to RLF, poor RF conditions, S1/backhaul instability, handover failures, or hardware issues. Improve RF coverage, verify S1 link, optimize HO parameters, and fix hardware/transport faults to reduce abnormal releases.Exclude ATDT in failed Sector and Redo again. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 3. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 4. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 5. MO CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 6. MT CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 7. Reselection Time After CSFB Call Idle to LTE (ms) 8. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | CHKBD2_BLG_P47 | L2100 | 08-Dec-2025 9:39 PM | FAIL | 1. Network Detach Success rate 2. Round trip time or Latency(ms) 3. CSFB success rate 4. Check functioning of ViLTE | 1. Static Cell Reselection 2. Static Ping 3. Static CSFB MO 4. Static Video call MO | 1. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 2. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 3. CSFB MO Success Rate failed because the Call Setup Time is above the acceptance criteria, or there are blocked/unsuccessful calls, or fewer than 3 successful calls were completed. Kindly redo the test ensuring CST is within limits and at least 3 MO CSFB calls are successfully established. 4. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | HLLUR1_BLG_P47 | L2100 | 08-Dec-2025 6:00 PM | FAIL | 1. TCP UL (Mbps) 2. Network Detach Success rate 3. Round trip time or Latency(ms) 4. Check functioning of ViLTE | 1. Static UL 2. Static Cell Reselection 3. Static Ping 4. Static Video call MO | 1. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 2. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 3. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 4. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | KJRUS1_BEN_P47 | L2100 | 08-Dec-2025 5:00 PM | FAIL | 1. Session establishment time(ms) 2. TCP UL (Mbps) 3. Network Detach Success rate 4. Round trip time or Latency(ms) 5. CSFB: MO call set up time 6. CSFB: MT call set up time 7. Fast Return Time 8. Check functioning of ViLTE | 1. Static ATDT 2. Static UL 3. Static Cell Reselection 4. Static Ping 5. Static CSFB MO 6. Static CSFB MT 7. Static CSFB MO 8. Static Video call MO | 1. Session Abnormal Release Rate failed due to RLF, poor RF conditions, S1/backhaul instability, handover failures, or hardware issues. Improve RF coverage, verify S1 link, optimize HO parameters, and fix hardware/transport faults to reduce abnormal releases.Exclude ATDT in failed Sector and Redo again. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 3. Exclude the current logfile and create a new one. Ensure that the Detach Request matches the Detach Accept. Verify this in the Event tab of AZQ before saving the logfile 4. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 5. MO CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 6. MT CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 7. Reselection Time After CSFB Call Idle to LTE (ms) 8. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script.
KK | MLGAN2_BID_P47 | L2100 | 09-Dec-2025 8:16 PM | FAIL | 1. Check functioning of ViLTE 2. Volte abnormal release rate , drop rate . Mention the cause code of abnormal release | 1. Static Video call MO 2. Drive Volte SCMO | 1. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script. 2. There is a call drop in the failed sector. Kindly exclude the affected logfile, create a new logfile, and redo the test to verify successful call completion with no drops.
KK | HEBLL1_BLG_P47 | L2100 | 09-Dec-2025 1:22 PM | FAIL | 1. TCP DL (Mbps) 2. TCP UL (Mbps) 3. Round trip time or Latency(ms) 4. CSFB: MO call set up time 5. CSFB: MT call set up time 6. Fast Return Time 7. Check functioning of ViLTE 8. Volte abnormal release rate , drop rate . Mention the cause code of abnormal release | 1. Static DL 2. Static UL 3. Static Ping 4. Static CSFB MO 5. Static CSFB MT 6. Static CSFB MO 7. Static Video call MO 8. Drive Volte SCMO | 1. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with good coverage, and use the Okhla Speedtest while running the script. 2. The peak value is not meeting the acceptance criteria. Please redo the static test in the site’s main lobe with strong coverage. While performing the UL static test, start uploading a long video on YouTube to ensure proper uplink loading. 3. The Ping is above the acceptance criteria , Kinldy Exclud the logfile and Create new and verify the ping should bhe 40 to 50 ms , before saving the logfile 4. MO CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 5. MT CSFB Call Setup Time (ms) is higher than the acceptance criteria. If the value appears as NA or 0, it indicates that the call was not successfully established. Kindly redo the test and verify the call setup time. 6. Reselection Time After CSFB Call Idle to LTE (ms) 7. Do not use WhatsApp for this test. Perform a manual VoLTE video call after running the script. 8. There is a call drop in the failed sector. Kindly exclude the affected logfile, create a new logfile, and redo the test to verify successful call completion with no drops.